## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | IOT Enabled Gas Leakage Detection System |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P Shah Institute of Technology
PROJECT GUIDE |  | Prof.Apeksha Mohite, Prof.Sonal Jain |  |  |  |  | DATE | [6 empty] | 2021-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Shailesh,Sankalp, Akash | 2020-01-20 | 2020-08-19 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T; WEEK 11 W to WEEK 11 F
1.1.1 | Research paper finalization | Shailesh,Sankalp | 2020-02-08 | 2020-08-20 | 3 | 100% | bar: WEEK 2 W; WEEK 11 W to WEEK 11 F
1.2 | Project Title | Shailesh,Sankalp, Akash | 2020-02-28 | 2020-09-01 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W; WEEK 11 W to WEEK 11 F
1.3 | Abstract | Shailesh | 2020-03-14 | 2020-09-01 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R; WEEK 11 W to WEEK 11 F
1.4 | Objectives | Shailesh,Sankalp | 2020-03-21 | 2020-09-30 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 11 W to WEEK 11 F
1.5 | Literature Review | Sankalp | 2020-03-28 | 2020-10-19 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R; WEEK 11 W to WEEK 11 F
1.6 | Problem Definition | Shailesh | 2020-03-05 | 2020-10-19 | 1 | 100% | bar: WEEK 3 F; WEEK 11 W to WEEK 11 F
1.7 | Scope | Shailesh | 2020-03-05 | 2020-10-19 | 1 | 100% | bar: WEEK 3 F; WEEK 11 W to WEEK 11 F
1.8 | Technology stack | Shailesh,Sankalp | 2020-03-05 | 2020-10-19 | 1 | 80% | bar: WEEK 3 F; WEEK 11 W to WEEK 11 F
1.9 | Benefits for environment | Shailesh | 2020-03-05 | 2020-10-19 | 1 | 100% | bar: WEEK 3 F; WEEK 11 W to WEEK 11 F
1.1 | Benefits for society | Shailesh | 2020-03-05 | 2020-10-20 | 1 | 80% | bar: WEEK 3 F; WEEK 11 W to WEEK 11 F
1.11 | Applications | Shailesh,Sankalp | 2020-03-05 | 2020-10-19 | 1 | 100% | bar: WEEK 3 F; WEEK 11 W to WEEK 11 F
2 | Project Design
2.1 | Proposed System | Shailesh,Sankalp | 2020-09-19 | 2020-10-19 | 2 | 100% | bar: WEEK 4 M to WEEK 4 R; WEEK 11 W to WEEK 11 F
2.2 | Design(Flow Of Modules) | Sankalp | 2020-09-19 | 2020-10-19 | 2 | 70% | bar: WEEK 4 R to WEEK 6 M; WEEK 11 W to WEEK 11 F
2.3 | Activity Diagram | Shailesh,Sankalp | 2020-09-19 | 2020-10-19 | 2 | 100% | bar: WEEK 6 M to WEEK 6 F; WEEK 11 W to WEEK 11 F
2.4 | Use Case Diagram | Shailesh,Sankalp | 2020-09-19 | 2020-10-19 | 2 | 100% | bar: WEEK 6 M to WEEK 6 F; WEEK 11 W to WEEK 11 F
2.5 | Description Of Use Case | Shailesh | 2020-09-19 | 2020-10-19 | 2 | 100% | bar: WEEK 4 M to WEEK 5 T; WEEK 11 W to WEEK 11 F
2.6 | Modules | bar: WEEK 11 W to WEEK 11 F
2.6.1 | Module-1 | Shailesh,Sankalp, Akash | 2020-09-19 | 2020-10-19 | 2 | 85% | bar: WEEK 11 W to WEEK 11 F
2.6.2 | Module-2 | Shailesh,Sankalp | 2020-09-19 | 2020-10-19 | 2 | 85% | bar: WEEK 5 W to WEEK 6 R; WEEK 11 W to WEEK 11 F
2.6.3 | Module-3 | Shailesh | 2020-09-19 | 2020-10-06 | 2 | 85% | bar: WEEK 11 W to WEEK 11 F
2.6.4 | Module-4 | Shailesh,Sankalp | 2020-09-19 | 2020-10-19 | 2 | 85% | bar: WEEK 5 M to WEEK 6 W; WEEK 11 W to WEEK 11 F
2.7 | Preparation Of Report | Shailesh,Sankalp,Akash | 2020-09-19 | 2020-10-06 | 2 | 100% | bar: WEEK 4 F to WEEK 7 M; WEEK 11 W to WEEK 11 F
3 | Project Implementation
3.1 | Module-1 | Shailesh,Sankalp | 2021-02-04 | 2021-02-04 | 0 | 80% | bar: WEEK 7 W to WEEK 8 R; WEEK 11 W to WEEK 11 F
3.2 | Module-2 | Shailesh | 2021-02-05 | 2021-02-05 | 0 | 80% | bar: WEEK 7 F to WEEK 8 F; WEEK 11 W to WEEK 11 F
3.3 | Module-3 | Sankalp | 2021-02-11 | 2021-02-12 | 0 | 75% | bar: WEEK 8 R to WEEK 9 T; WEEK 11 W to WEEK 11 F
3.4 | Module-4 | Shailesh,Sankalp | 2021-02-25 | 2021-02-26 | 0 | 80% | bar: WEEK 8 F to WEEK 10 R; WEEK 11 W to WEEK 11 F
4 | Testing
4.1 | Design of Test Cases | Shailesh,Sankalp | 2021-03-03 | 2021-03-09 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F; WEEK 9 F to WEEK 10 F; WEEK 11 W to WEEK 11 F
4.2 | Architecture | Shailesh,Sankalp | 2021-03-10 | 2021-03-16 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 10 W to WEEK 12 W
4.3 | Prototyping | Shailesh | 2021-03-17 | 2021-03-23 | 1 | 50% | bar: WEEK 1 T to WEEK 1 F; WEEK 10 W to WEEK 12 W
4.4 | Development | Shailesh | 2021-03-24 | 2021-03-30 | 1 | 80% | bar: WEEK 1 T to WEEK 1 F; WEEK 11 M to WEEK 12 M
4.5 | Testing QA | Shailesh,Sankalp | 2021-03-31 | 2021-04-06 | 1 | 50% | bar: WEEK 1 T to WEEK 1 F; WEEK 11 W to WEEK 12 W
4.6 | Configuration Of Dashboard | Shailesh,Sankalp | 2021-04-14 | 2021-04-20 | 1 | 70% | bar: WEEK 1 T to WEEK 1 F; WEEK 11 T to WEEK 12 R
4.7 | Worked on web server | Sankalp | 2021-04-21 | 2021-04-27 | 1 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 11 T to WEEK 12 R
4.8 | Implementation of Web Server | Sankalp | 2021-04-21 | 2021-04-27 | 1 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 11 M to WEEK 12 W
4.9 | Implementation of Hardware | Shailesh,Sankalp | 2021-04-28 | 2021-05-04 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 11 W to WEEK 12 F
4.1 | Configuration Of Hardware through which Modules will be connected | Shailesh,sankalp | 2021-05-05 | 2021-05-11 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 11 W to WEEK 11 F; WEEK 12 T to WEEK 12 F
5 | Results and Analyis
5.1 | Report Preparation | Shailesh,Sankalp,Akash | 2021-02-25 | 2021-02-26 | 1 | 90% | bar: WEEK 7 T to WEEK 8 W; WEEK 10 R to WEEK 12 R
5.2 | Graphical Representation | Shailesh | 2021-03-24 | 2021-03-26 | 1 | 70% | bar: WEEK 12 M to WEEK 12 R